## Sheet1
sortscore: Development, Usage, and Publication
Development Stage 1: Single oligo scoring
Task | Status | Notes
Add console command to run sortscore | TRUE | sortscore -c config.json
Custom instructions for AI | TRUE
Make virtual environment and install sortscore | TRUE | source venv & pip install -e
Scaffold config files and experiment definition | TRUE
Refactor scoring notebook | TRUE
Add dataclass for handling separate experiments | TRUE
Add oPool5b test data and generate configs | TRUE
Add logic to handle AA or DNA variant data | TRUE
Validate with existing GLI2 analysis | TRUE
Normalize technical replicates | TRUE
Quality metrics: SD, CV, SE, CI | TRUE | *** might consider use for "misbehaving" variants
Pool codon and replicate variance | TRUE | checking logic
Output heatmap | TRUE
Output scores | TRUE
Add filtering on quality with user provided threshold | FALSE | Flag and include in final scores table, but don't use to create heatmap. User option for turning off filtering
Allow alphanumeric bin names | TRUE | added logic to handle letters
Testing: OTX2 Analysis
Task | Status | Notes
Get counts data if already available | TRUE
Convert parquet files to gzipped csv | TRUE | check polars package
Config files | TRUE
Clean data | TRUE | already processed
Run sortscore | TRUE | debugged
Review analysis notebook they have | TRUE | Could run up to data VEPs
Check wt sequence | TRUE | Isoform 2 on Uniprot
Compare heatmaps | TRUE
DNA level or only AA level mutagenesis library? | FALSE | Reprocess reads if DNA level? Or find unaggregated file?
Review OTX2 data quality | FALSE
Quality filtering - codons, reps CV > 50%? | FALSE
Additional replicates required? | FALSE
Review notes from lab meeting about further analysis | FALSE | See Michael's msg
Add rep activity correlations | FALSE | Michael also has per variant correlations, checking barcode representation across bins?
Histogram of scores | FALSE
Scatterplots | FALSE
Meet with Barack and Michael to discuss next steps | FALSE
Testing: CRX Analysis
Task | Status | Notes
Get counts data if already available | TRUE | Dustin moved to scratch
Convert parquet files to gzipped csv | FALSE | use sortscore
Config files | FALSE | get wt sequence from notebook, counts from logs
Clean data | TRUE | already processed
Run sortscore | FALSE
Review analysis notebook they have | FALSE
Check wt sequence | FALSE
Compare heatmap with published figure | FALSE
DNA level or only AA level mutagenesis library? | FALSE | Reprocess reads if DNA level? Or find unaggregated file?
Review data quality | FALSE
Quality filtering | FALSE
Rep correlations | FALSE | Before and after filtering
Histogram of scores | FALSE
Scatterplots | FALSE
Development Stage 2: Normalization (across oligos, etc)
Task | Status | Notes
Add GLI2_DBD_B test data and generate configs | TRUE
Test minimum read threshold | TRUE
Output technical replicate scatterplots | FALSE | before and after filtering
Convert normalization notebook | FALSE
Test logic to generate full heatmaps | FALSE
Validate using GLI2 B scores and figures | FALSE
Development Stage 3: Document and Release
Task | Status | Notes
Generate initial pass of package documentation | TRUE
Fix or remove codon weighting | FALSE
Check pooled SEM calculation | FALSE
Update docs: Batch normalization across oligos, leave averaging separate experiments (biological reps) to the user | FALSE
External testers | FALSE | Grad student? Could msg working group
Check | FALSE
Clean up test files | FALSE
Add unit tests | FALSE
Publish package, test download | FALSE
FALSE
Paper
Task | Status | Notes
Initial diagram of high level package steps | TRUE
Determine target journal | FALSE
Use allofus package paper format | FALSE
Final pass of diagram with actual function names and workflow | FALSE
Table of function, description, problem it solves | FALSE
Example data (CRX) | FALSE
Show performance of filtering steps | FALSE
Equations | FALSE | See overleaf doc
First draft | FALSE
Discuss incorporating into MaveDB | FALSE
Other improvements
Task | Status | Notes
Map barcodes to variants | FALSE
Processing fastq instructions | FALSE
Take in output from DimSum? | FALSE
Linear mixed model with random effects | FALSE | Random effect terms: tech rep, codons, residual variance
Using stats file | FALSE | Print output, add correlations before/after filtering
Flag low confidence variants on the heatmap if they aren't filtered out | FALSE | Red corner
SGE plot (1 nucleotide change) | FALSE
P values for variants (no multiple test correction) | FALSE

## OTX2_info
8 samples, 4 bins, 2 bio reps | log (203936## jobs) | Reads (after filtering) | Reads (before filtering) | counts files
OTRA-1A | clean_reads.20393616.1 | 57079872 | 57295729 | /Users/c.chitwood/code/sortscore/tests/OTX2/Barcodes/OTRA-1A.extracted_barcodes.counts.parquet
OTRA-1B | clean_reads.20393617.2 | 38997625 | 39086796 | /Users/c.chitwood/code/sortscore/tests/OTX2/Barcodes/OTRA-1B.extracted_barcodes.counts.parquet
OTRA-1C | clean_reads.20393618.3 | 43970598 | 44059489 | /Users/c.chitwood/code/sortscore/tests/OTX2/Barcodes/OTRA-1C.extracted_barcodes.counts.parquet
OTRA-1D | clean_reads.20393619.4 | 51214537 | 51319515 | /Users/c.chitwood/code/sortscore/tests/OTX2/Barcodes/OTRA-1D.extracted_barcodes.counts.parquet
OTRA-2A | clean_reads.20393620.5 | 44644058 | 44754126 | /Users/c.chitwood/code/sortscore/tests/OTX2/Barcodes/OTRA-2A.extracted_barcodes.counts.parquet
OTRA-2B | clean_reads.20393621.6 | 50590118 | 50712006 | /Users/c.chitwood/code/sortscore/tests/OTX2/Barcodes/OTRA-2B.extracted_barcodes.counts.parquet
OTRA-2C | clean_reads.20393622.7 | 47513811 | 47667963 | /Users/c.chitwood/code/sortscore/tests/OTX2/Barcodes/OTRA-2C.extracted_barcodes.counts.parquet
OTRA-2D | clean_reads.20393615.8 | 35165584 | 35232194 | /Users/c.chitwood/code/sortscore/tests/OTX2/Barcodes/OTRA-2D.extracted_barcodes.counts.parquet
Barcode to variant counts
/Users/c.chitwood/code/sortscore/tests/OTX2/notebook/OTX2_Library_Step_3_180.barcode_to_variant_map.tsv